## Tasks
Task | Priority | Owner | Status | Start date | End date | Milestone | Deliverable | Notes
Create Migrations (All) | Medium | duonggt.124010124038@vtc.edu.vn | Completed | 2025-11-27 | 2025-11-28
Create Models (All) | Medium | anmd.124010124106@vtc.edu.vn | Completed | 2025-11-29 | 2025-11-30
Create Client Controller (All) Part-1 | Medium | minhnk.124010123042@vtc.edu.vn | Completed | 2025-12-09 | 2025-12-12
Create Client Controller (All) Part-2 | Medium | nghiahd.125010124008@vtc.edu.vn | In progress | 2025-12-13 | 2025-12-16
Cross check project | Medium | duonggt.124010124038@vtc.edu.vn | In progress | 2025-12-17 | 2025-12-20
Design Client Frontend Part-1 | Medium | duonggt.124010124038@vtc.edu.vn | In progress | 2025-12-21 | 2025-12-22
Design Client Frontend Part-2 | Medium | anmd.124010124106@vtc.edu.vn | In progress | 2025-12-23 | 2025-12-24
Build Client Frontend Part-1 | Medium | minhnk.124010123042@vtc.edu.vn | In progress | 2025-12-25 | 2026-01-06
Build Client Frontend Part-2 | Medium | nghiahd.125010124008@vtc.edu.vn | In progress | 2025-12-25 | 2026-01-06

## Functions
Code | Functions | Description | Entity | Models | Database | Diagram
U-101 | Register | 1. Input: name, email, password, password_confirmation 2. Validate: name required, email required + unique, password rules + confirmed 3. Hash password (via model cast) và tạo user 4. Trả về redirect/ session | Customer | User | users | Sequence
U-102 | Login | 1. Input: email, password 2. Validate: fields required 3. Compare credentials với DB (hashed password) 4. Tạo session; nếu chọn Remember -> set remember_token 5. Redirect tới Dashboard/Home | Customer | User | users | Sequence
U-103 | Logout | 1. Input: (POST logout form) 2. Invalidate session, regenerate token 3. Redirect về Home | Customer | User | (session / cookies) | Activity
U-104 | Forgot password (Request reset link) | 1. Input: email 2. Validate: email format / tồn tại (Fortify xử lý) 3. Tạo token reset (password_resets) hoặc tạo link có token 4. Gửi email chứa link reset; trả status thành công | Customer | User | password_resets (or signed link) | Sequence
U-105 | Reset password | 1. Input: token, email, new password, password_confirmation 2. Validate: token hợp lệ và mật khẩu theo quy tắc 3. Update users.password (hash) và xóa token/expire link 4. Redirect/notify | Customer | User | users, password_resets | Sequence
U-106 | Verify email / Resend verification | 1. Action: resend verification request hoặc user click verify link 2. Gửi link xác thực ký (signed) hoặc kiểm tra signature khi verify 3. Khi verify success -> set email_verified_at trên users | Customer | User | users (email_verified_at) | Sequence
U-107 | Profile — Edit / Update / Destroy | 1. Edit: hiển thị profile hiện tại 2. Update: Input name, email; Validate name required, email unique; Nếu đổi email -> set email_verified_at = null + gửi verification 3. Destroy: Input password confirm -> validate current_password; logout, delete user, invalidate session | Customer | User | users | Sequence
U-108 | Change account password | 1. Input: current_password, password, password_confirmation 2. Validate current_password + password rules 3. Update password (hashed) vào users | Customer | User | users | Sequence
U-109 | Two-factor authentication (2FA) | 1. Enable 2FA: generate secret & recovery codes; show QR 2. User verify OTP -> backend lưu two_factor_secret, two_factor_recovery_codes, set two_factor_confirmed_at 3. Disable / manage codes accordingly | Customer | User | users (two_factor_secret, two_factor_recovery_codes, two_factor_confirmed_at) | Sequence
U-110 | Confirm password (sensitive actions) | 1. Input: current_password 2. Middleware password.confirm / ConfirmablePasswordController validate password 3. Nếu đúng -> cho phép thực hiện hành động nhạy cảm | Customer | User | users | Activity
U-111 | Home / Dashboard (auth + verified) | 1. Route: / (welcome) & /dashboard (auth + verified middleware) 2. Nếu auth & verified -> hiển thị dashboard; nếu không -> redirect login | User (authenticated) | User | users | Page / Activity